## Keys and Definitions
Status
Level | Description
0. Challenge/feedback logged | Challenge/feedback raised, action under delibertation.
1. Initiated | Need identified and planning has commenced.
2. Implementing | Implementation plans have started.
3. Completed | Steps are completed, and no further action is required by the organisation(s).
4. Not initiated | Reflects progress of steps that have been considered by the organisation(s) but are not currently planned for further implementation.
Raised by
Category | Sub-category
Flexibility providers | Supplier, trade or representative body, aggregator, generator, storage, demand customer.
Supply chain and smart solutions
Platform provider
Settlement agent
Community, local energy and local authorities
Data
Academia
Government
Consumer protection party
Independent Chair

## Key feedback
Challenge Group feedback log
Feedback no. | Date raised | Feedback name | Feedback description | Groups affected | Status | Recommended action | Progress and closing comments
1 | 2023-03-01 | Industry developments | Challenge Group flagged open Ofgem CFI on the Future of Distributed Flexibility and consultation on Local Energy Institutions and Governance. | Steering Group | 3. Completed | Steering Group discussing impact on ON. | ENA response submitted to CFI and consultation.
2 | 2023-03-01 | Service failure penalties | Capacity to deliver a service can change closer to delivery time where services have been procured long in advance. Providers may find it helpful to have more clarity on when liabilities for service failure kick in. | Standard Agreement | 3. Completed | Technical working group discussing feedback. | Ver 3.0 of Standard Agreement published in April 2024.
3 | 2023-03-01 | Aligned flexibility products | • Separate product definitions should be created where there are large differences, however, this should be balanced with not creating too many individual products. • A set of standard products will allow providers to more easily set up operational systems for engaging wiith different products and providers. • Community Energy organisations are still in the process of defining how they will participate as providers. It is likely that additional feedback on how product specifications affect them will emerge later. | Flexibility Products | 3. Completed | Technical working group developing product definitions and recommendations for alignment. | Updated flexibility product definitions have been published. A process for retiring products that are not in frequent use is in progress.
4 | 2023-03-01 | Increment 1 Primacy Rules | The Primacy Rules working group should keep the Ofgem CFI on Distributed Flexibility in mind in case this has implications for Primacy. The Group noted speed of deployment as a priority. | Primacy Rules | 3. Completed | Technical working group discussing feedback. | Primacy will keep an eye on any relevant outcomes of the CFI. They are keen to engage with Ofgem throughout the development of further primacy iterations. Discussions are currently underway at Steering group, with regards to resources required to accelerate the development of further Primacy Rule iterations.
5 | 2023-03-01 | ENA's response to Ofgem consultation and CFI | The Group would like an update on ENA’s response to Ofgem CFI on the Futue of Distributed Flexibility and consultation on Local Energy Institutions and Governance. | ON Programme | 3. Completed | ENA are developing their response and will share an update at the next Challenge Group meeting. | ENA reponse has been shared.
6 | 2023-03-01 | Engagement with other ENA groups | Challenge Group are lookig to confirm ways for stakeholders to engage with groups across the wider ENA. | ENA | 3. Completed | The query has been raised within ENA. | ENA will be moving to a new newsletter format with stakeholders able to select categories of interest across ENA for regular updates, including events and other engagement opportunities.
7 | 2023-05-04 | Reporting frequency | The Challenge Group noted that it could be useful to have a breakdown of each working group’s activity and monthly reporting of each workstream. | ENA | 3. Completed | Monthly visibility of progress was made availalable to the Challenge Group members. | Monthly visibility of progress was made availalable to the Challenge Group members.
8 | 2023-05-04 | In-depth engagement | It could be beneficial to have industry engagement with specific workstreams and technical working groups. | ENA | 3. Completed | If Challenge Group members wish to participate in any of the ON technical working groups in any way this would be happily accommodated and input appreciated. ENA will also be hosting two focus group days in July 2023 to facilitate industry-wide in-depth input. | If Challenge Group members wish to participate in any of the ON technical working groups in any way this would be happily accommodated and input appreciated. Working groups will be opened to focus groups and consultations as appropriate.
9 | 2024-09-21 | Flex product governance | Once agreed, new flex product definitions should have a governance and change process to avoid future deviation. | Flexibility Products | 2. Implementing | The working group are developing a process for retiring products not in frequent use. Wider governance being considered as part of ON-wide governance arrangements. | Governance and change process development ongoing.
10 | 2024-09-21 | Dispatch API | FSPs can have different preferences when it comes to having multiple more frequent updates to an API vs one update that takes longer to create. There should be sufficient industry engagement to support a decision. | Dispatch Interoperability | 2. Implementing | Carry out additional stakeholder engagement to ensure FSP buy in to the proposed approach. | Engagement with FSPs and development of a proposal for dispatch API alignment ongoing.
11 | 2024-11-02 | Increment 2 Primacy Rules | Touch point with ANM visibility and technical limits was flagged. | Primacy Rules | 2. Implementing | Touch point to be discussed with ENA Strategic Connections Group. | Work ongoing with ENA Strategic Connections Group and DNV.
12 | 2024-11-02 | Asset registration duplication | Currently the responsibility for ensuring an asset is not already registered with another DNO for a service is with the provider. DNOs and ESO should consider whether there is a more central way of ensuring this that is less arduous for providers. | Standard Agreement | 4. Not initiated | Feedback noted and flagged as not a part of a current ON working group. | Feedback noted for future work.
13 | 2024-02-19 | Payment for multiple benefits | Where an FSPs response provides multiple benefits to the grid at both DSO and ESO level, payment for both benefits provided should be considered. | Stackability | 1. Initiated | There is currently no aligned view on this, which will need to be developed in collaboration with Ofgem, DESNZ, ESO and DSOs to then consider how to deliver the end goal operationally.
14 | 2024-05-09 | Flex Products & Stackability | Challenge Group noted a high interest in the process for retiring products. | Flex Products & Stackability | 1. Initiated | Technical Working Group developing process for retiring products. This will be shared with Challenge Group once available.
15 | 2024-05-09 | Dispatch API | Challenge Group noted that implementation timelines may be long and requested more clarity on next steps and milestones. | Dispatch Interoperability | 1. Initiated | Technical Working Group developing a more detailed timeline to be shared with Challenge Group.
16 | 2024-06-19 | Settlement Process | Challenge Group asked if there has been analysis done via DNOs on procured services and what was delivered against them. | Settlement Process | 1. Initiated | Technical Working Group have taken this away for additional data points to be considered within the analysis.
17 | 2024-06-19 | Settlement Process | Challenge Group asked what the validation for the same grace factor for all services is. | Settlement Process | 1. Initiated | Technical Working Group have taken this feedback away for further information.

## Challenges
Challenge log
Challenge no. | Date raised | Challenge name | Challenge description | Unanimous | Workstream and technical working groups affected | Status | Recommended action | Expected Resolution Timeframe | Outcome | Progress and closing comments